## Overview
Huckleberry VFX Vendor Weekly Report
Vendor: | RVX
Date: | {date}
For Week Ending: | {week_ending}
OVERALL ASSET & SHOT STATUS
Total Assets: |  |  |  | Total Shots:
Total Assets Turned over: |  | 0 | 0% | Total Shots Turned Over: | 0 | 0%
In Progress: |  | 0 | 0% | In Progress: | 0 | 0%
Awaiting Material: |  | 0 | 0% | Awaiting Material: | 0 | 0%
Omits: |  | 0 | 0% | Omits: | 0 | 0%
On Hold: |  | 0 | 0% | On Hold: | 0 | 0%
Pending Review: |  | 0 | 0% | Pending Review: | 0 | 0%
Final pending QC: |  | 0 | 0% | Proposed Final: | 0 | 0%
Finals: |  | 0 | 0% | Final pending QC: | 0 | 0%
CBBs: |  | 0 | 0% | Finals: | 0 | 0%
|  |  |  | CBBs: | 0 | 0%
WEEKLY SHOT STATUS UPDATES
Official Counts Received this week: |  |  | 0
Shots Omitted this week: |  |  | 0
Shots added this week: |  |  | 0
Shots submitted for Comp Finals this week: |  |  | 0
Finals received this week: |  |  | 0
Finals with Tech Fix Received this week: |  |  | 0
CBBs received this week: |  |  | 0

## Shots
Date | Type | Link | Vendor Status | Shared | % Complete | Next Submission Date | Turnover Date | Layout Blocking Date | Layout Final Date | Anim Blocking Date | Anim Final Date | FX Blocking | FX Final | Comp 1st Pass Date | Comp WIP Date | Proposed Creative Final Date | Final Delivery Date | Notes | Latest Version | Weekly Report
|  | 506_001_CTN_0500 | Approved | No | 60% | 2025-11-03 | 2025-07-28
|  | 506_001_CTN_0510 | Approved | No | 40% | 2025-11-07 | 2025-07-28
|  |  |  | No |  | 2025-10-23 | 2025-10-22
|  | 506_003_ITP_0010 | Approved | No | 50% | 2025-11-14 | 2025-09-02
|  | 506_003_ITP_0020 | Approved | No | 60% | 2025-11-04 | 2025-09-03
|  | 506_005_ITP_0200 | Approved | No | 70% | 2025-11-12 | 2025-09-04
|  | 506_005_ITP_0210 | Approved | No | 70% | 2025-11-12 | 2025-09-05
|  | 506_019_FAC_0010 | Approved | No | 40% | 2026-01-09 | 2025-09-03
|  | 506_031_CLT_0010 | Approved | No | 50% |  | 2025-09-04
|  | 506_032_CLT_0070 | Approved | No | 40% | 2025-11-21 | 2025-09-05
|  | 506_032_CLT_0100 | Approved | No | 50% | 2025-11-21 | 2025-09-06
|  | 506_032_CLT_0120 | Approved | No | 50% | 2025-11-21 | 2025-09-07
|  | 506_032_CLT_0130 | Approved | No | 30% | 2025-11-21 | 2025-09-08
|  | 506_032_CLT_0140 | Approved | No | 60% | 2025-11-21 | 2025-09-09
|  | 506_032_CLT_0150 | Approved | No | 40% | 2025-11-21 | 2025-09-10
|  | 506_032_CLT_0160 | Approved | No | 50% | 2025-11-21 | 2025-09-11
|  | 506_032_CLT_0170 | Approved | No | 50% | 2025-11-21 | 2025-09-12
|  | 506_032_CLT_0180 | Approved | No | 50% | 2025-11-21 | 2025-09-13
|  | 506_032_CLT_0190 | Approved | No | 50% | 2025-11-21 | 2025-09-14
|  | 506_032_CLT_0200 | Approved | No | 50% | 2025-11-21 | 2025-09-15
|  | 506_033_CLT_0300 | Approved | No | 50% | 2025-11-14 | 2025-09-16
|  | 506_033_CLT_0310 | Approved | No | 40% | 2025-11-07 | 2025-09-17
|  | 506_033_CLT_0320 | Approved | No | 60% | 2025-10-31 | 2025-09-18
|  | 506_033_CLT_0330 | Approved | No | 40% | 2026-01-16 | 2025-09-19
|  | 506_033_CLT_0340 | Approved | No | 40% | 2025-12-12 | 2025-09-20
|  | 506_033_CLT_0350 | Approved | No | 40% | 2025-12-12 | 2025-09-21
|  | 506_033_CLT_0360 | Approved | No | 40% | 2025-12-12 | 2025-09-22
|  | 501_013_MME_0500 | Approved | No | 10% | 2025-11-18 | 2025-07-11
|  | 505_018_ILF_0500 | Approved | No | 50% | 2025-11-14 | 2025-09-26
|  | 505_021_ILF_0510 | Approved | No | 40% | 2025-11-07 | 2025-09-26
|  | 505_021_ILF_0520 | Approved | No | 40% | 2025-11-07 | 2025-09-26
|  | 505_024_BTM_0500 |  | No | 10% | 2025-11-28 | 2025-10-10
|  | 506_003_ITP_0009 | Approved | No | 10% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0030 | Approved | No | 10% | 2025-11-14 | 2025-10-16
|  | 506_003_ITP_0040 | Approved | No | 10% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0050 | Approved | No | 50% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0055 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0060 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0070 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0110 | Approved | No | 50% | 2025-11-14 | 2025-10-16
|  | 506_003_ITP_0115 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0120 | Pending | No | 50% | 2025-11-07 | 2025-10-16
|  | 506_005_ITP_0145 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0150 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0160 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0180 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0190 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0195 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0240 | Approved | No | 15% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0250 | Approved | No | 15% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0260 | Approved | No | 15% | 2025-12-19 | 2025-10-16
|  | 506_023_CFL_0240 | Approved | No | 25% | 2025-12-19 | 2025-10-16
|  | 506_023_CFL_0250 | Approved | No | 25% | 2025-12-19 | 2025-10-16
|  | 506_023_CFL_0260 | Approved | No | 25% | 2025-12-19 | 2025-10-16
|  | 506_032_CLT_0010 | Approved | No | 30% | 2025-11-21 | 2025-10-16
|  | 506_032_CLT_0030 | Approved | No | 30% | 2025-11-21 | 2025-10-16
|  | 506_032_CLT_0060 | Approved | No | 10% | 2025-11-21 | 2025-10-16
|  | 503_029_FAF_0010 | Approved | No | 10% |  | 2025-10-21
|  | 506_001_CTN_0010 | Approved | No | 20% | 2025-11-28 | 2025-10-21
|  | 506_001_CTN_0020 | Approved | No | 20% | 2025-11-28 | 2025-10-21
|  | 506_003_ITP_0075 | Approved | No | 20% | 2025-11-14 | 2025-10-21
|  | 506_003_ITP_0130 | Approved | No | 10% |  | 2025-10-21
|  | 506_005_ITP_0140 | Approved | No |  |  | 2025-10-21
|  | 506_019_FAC_0020 | Approved | No | 10% | 2025-12-19 | 2025-10-21
|  | 506_021_CFL_0012 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0015 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0017 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0019 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0030 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_033_CLT_0250 |  | No
|  | 505_018_ILF_0020 |  | No |  |  | 2025-10-30
|  | 505_018_ILF_0030 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0050 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0060 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0070 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0080 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0090 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0100 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0110 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0120 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0130 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0140 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0150 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0160 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0180 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0190 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0200 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0210 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0220 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0230 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0240 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0250 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0270 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0280 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0290 |  | No |  |  | 2025-10-30
|  | 506_003_ITP_0010 | Approved | No | 50% | 2025-11-14 | 2025-09-02
|  | 506_003_ITP_0020 | Approved | No | 60% | 2025-11-04 | 2025-09-03
|  | 506_005_ITP_0200 | Approved | No | 70% | 2025-11-12 | 2025-09-04
|  | 506_005_ITP_0210 | Approved | No | 70% | 2025-11-12 | 2025-09-05
|  | 506_019_FAC_0010 | Approved | No | 40% | 2026-01-09 | 2025-09-03
|  | 506_031_CLT_0010 | Approved | No | 50% |  | 2025-09-04
|  | 506_032_CLT_0070 | Approved | No | 40% | 2025-11-21 | 2025-09-05
|  | 506_032_CLT_0100 | Approved | No | 50% | 2025-11-21 | 2025-09-06
|  | 506_032_CLT_0120 | Approved | No | 50% | 2025-11-21 | 2025-09-07
|  | 506_032_CLT_0130 | Approved | No | 30% | 2025-11-21 | 2025-09-08
|  | 506_032_CLT_0140 | Approved | No | 60% | 2025-11-21 | 2025-09-09
|  | 506_032_CLT_0150 | Approved | No | 40% | 2025-11-21 | 2025-09-10
|  | 506_032_CLT_0160 | Approved | No | 50% | 2025-11-21 | 2025-09-11
|  | 506_032_CLT_0170 | Approved | No | 50% | 2025-11-21 | 2025-09-12
|  | 506_032_CLT_0180 | Approved | No | 50% | 2025-11-21 | 2025-09-13
|  | 506_032_CLT_0190 | Approved | No | 50% | 2025-11-21 | 2025-09-14
|  | 506_032_CLT_0200 | Approved | No | 50% | 2025-11-21 | 2025-09-15
|  | 506_033_CLT_0300 | Approved | No | 50% | 2025-11-14 | 2025-09-16
|  | 506_033_CLT_0310 | Approved | No | 40% | 2025-11-07 | 2025-09-17
|  | 506_033_CLT_0320 | Approved | No | 60% | 2025-10-31 | 2025-09-18
|  | 506_033_CLT_0330 | Approved | No | 40% | 2026-01-16 | 2025-09-19
|  | 506_033_CLT_0340 | Approved | No | 40% | 2025-12-12 | 2025-09-20
|  | 506_033_CLT_0350 | Approved | No | 40% | 2025-12-12 | 2025-09-21
|  | 506_033_CLT_0360 | Approved | No | 40% | 2025-12-12 | 2025-09-22
|  | 501_013_MME_0500 | Approved | No | 10% | 2025-11-18 | 2025-07-11
|  | 505_018_ILF_0500 | Approved | No | 50% | 2025-11-14 | 2025-09-26
|  | 505_021_ILF_0510 | Approved | No | 40% | 2025-11-07 | 2025-09-26
|  | 505_021_ILF_0520 | Approved | No | 40% | 2025-11-07 | 2025-09-26
|  | 505_024_BTM_0500 |  | No | 10% | 2025-11-28 | 2025-10-10
|  | 506_003_ITP_0009 | Approved | No | 10% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0030 | Approved | No | 10% | 2025-11-14 | 2025-10-16
|  | 506_003_ITP_0040 | Approved | No | 10% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0050 | Approved | No | 50% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0055 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0060 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0070 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0110 | Approved | No | 50% | 2025-11-14 | 2025-10-16
|  | 506_003_ITP_0115 | Approved | No | 20% | 2025-11-21 | 2025-10-16
|  | 506_003_ITP_0120 | Pending | No | 50% | 2025-11-07 | 2025-10-16
|  | 506_005_ITP_0145 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0150 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0160 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0180 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0190 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0195 | Approved | No | 40% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0240 | Approved | No | 15% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0250 | Approved | No | 15% | 2025-12-19 | 2025-10-16
|  | 506_005_ITP_0260 | Approved | No | 15% | 2025-12-19 | 2025-10-16
|  | 506_023_CFL_0240 | Approved | No | 25% | 2025-12-19 | 2025-10-16
|  | 506_023_CFL_0250 | Approved | No | 25% | 2025-12-19 | 2025-10-16
|  | 506_023_CFL_0260 | Approved | No | 25% | 2025-12-19 | 2025-10-16
|  | 506_032_CLT_0010 | Approved | No | 30% | 2025-11-21 | 2025-10-16
|  | 506_032_CLT_0030 | Approved | No | 30% | 2025-11-21 | 2025-10-16
|  | 506_032_CLT_0060 | Approved | No | 10% | 2025-11-21 | 2025-10-16
|  | 503_029_FAF_0010 | Approved | No | 10% |  | 2025-10-21
|  | 506_001_CTN_0010 | Approved | No | 20% | 2025-11-28 | 2025-10-21
|  | 506_001_CTN_0020 | Approved | No | 20% | 2025-11-28 | 2025-10-21
|  | 506_003_ITP_0075 | Approved | No | 20% | 2025-11-14 | 2025-10-21
|  | 506_003_ITP_0130 | Approved | No | 10% |  | 2025-10-21
|  | 506_005_ITP_0140 | Approved | No |  |  | 2025-10-21
|  | 506_019_FAC_0020 | Approved | No | 10% | 2025-12-19 | 2025-10-21
|  | 506_021_CFL_0012 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0015 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0017 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0019 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_021_CFL_0030 | Approved | No | 10% | 2025-11-28 | 2025-10-21
|  | 506_033_CLT_0250 |  | No
|  | 505_018_ILF_0020 |  | No |  |  | 2025-10-30
|  | 505_018_ILF_0030 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0050 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0060 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0070 |  | No |  |  | 2025-10-30
|  | 505_019_ILF_0080 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0090 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0100 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0110 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0120 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0130 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0140 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0150 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0160 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0180 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0190 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0200 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0210 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0220 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0230 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0240 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0250 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0270 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0280 |  | No |  |  | 2025-10-30
|  | 505_021_ILF_0290 |  | No |  |  | 2025-10-30

## Assets
Date | Type | Link | Vendor Status | Shared | % Complete | Next Submission Date | Model Blocking | Model Final | Rig Final | Lookdev Final | FX Blocking | Env Blocking | Asset Final | Notes | Latest Version | Weekly Report
mcCliffs
montecalvo
mcBailey
mcBarbican
mcCourtyard
mcEnv
mcKeep
mcTower
mcTrees
mcWalls
mcWaterTower
bagPile
bags
banner
barrel
barrelCluster
bench
boulder
box
boxCluster
brazier
bucket
candle
carpet
carryBundle
cartDestroyed
cartMarket
cartWheel
cartWithBags
cauldron
chair
cluster
coverFabric
craneWheel
desk
firepit
gakBarrelCluster
gakBoxCluster
gibbet
lantern
luggage
marketFood
pebble
rockingChair
ropeBundle
sailcloth
sign
stool
table
tarp
tent
vase
wallTorch
weaponsRack
mcArmory
|  | tnlGardens |  |  |  |  | 2025-08-07
|  | tnlPalace |  |  |  | 2025-11-07 | 2025-08-07
|  | tnlFlowers |  |  |  |  | 2025-08-07
tnlPalaceScan
tnlPalaceEredinsQuartersScan
tnlPalaceHallwayScan
grassFieldGrass
grassStraw
grassGreatBrome
treeWhiteFir
treeHorseChestnut
treeEuropeanLinden
shrubBrush
shrubForestBrush
shrubForestBush
shrubShrub
shrubWeedClump
|  | tnlPalaceInt |  |  |  |  | 2025-08-07
unicornHornScan
|  | Fog |  |  |  |  | 2025-09-26
|  | OpxCollarChain |  |  |  | 2025-11-07 | 2025-10-14
X6_33D
X6_33F
X6_33N
orpyxDogCollarScan
5_18C
5_21V
X5_21P
unicornHorn
|  | tnlDust |  |  |  |  | 2025-10-21
|  | tnlMagic |  |  |  |  | 2025-10-21
|  | tnlHeather |  |  |  |  | 2025-10-21